## Sheet1
BackLog - schedule planning
operation | expected schedule | real schedule
model class conception | 4 hours | 2 hours
implementation Model | 5 hours | 5 hours
build MVC struct | 2 days | 2 days
create restaurant template | 2 days | 2 days
modal restaurant details | 1 day | 1 dat
modal restaurant create/edit | 1 day | 2 days
security implementation | todo
test battery | 7 days | in_progress
understand theamleaf problem | 2 days | 7 days
exception handler | 2 days | in_progress
global CSS | 2 days | in_progress
bind employees to restaurants | 1 day | 2 days
role implementation | 2 days | todo
search list | 3 hours | 2 hours